## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Set up project environment and configure Spark server for application execution | MUST HAVE | No Dependency | Adesh Sonawane | 3- Completed
S1 | S1 | US-02 | Create Account model and build repository layer for data management | MUST HAVE | No Dependency | Adesh Sonawane | 3- Completed
S2 | S2 | US-03 | Develop API to create new accounts with proper input handling | MUST HAVE | US-02 | Adesh Sonawane | 3- Completed
S3 | S3 | US-04 | Build API to retrieve account details using unique account ID | MUST HAVE | US-03 | Adesh Sonawane | 3- Completed
S3 | S3 | US-05 | Implement feature to fetch and display all account records | MUST HAVE | US-02 | Adesh Sonawane | 3- Completed
S4 | S4 | US-06 | Develop deposit functionality with correct balance update logic | MUST HAVE | US-03 | Adesh Sonawane | 3- Completed
S5 | S5 | US-07 | Create withdrawal feature with proper validation and checks | MUST HAVE | US-06 | Adesh Sonawane | 3- Completed
S5 | S5 | US-08 | Implement money transfer functionality between accounts | MUST HAVE | US-07 | Adesh Sonawane | 3- Completed
S6 | S6 | US-09 | Add validation rules and exception handling for transactions | MUST HAVE | US-08 | Adesh Sonawane | 3- Completed
S7 | S7 | US-10 | Develop balance alert feature for monitoring minimum threshold | SHOULD HAVE | US-02 | Adesh Sonawane | 3- Completed
S7 | S7 | US-11 | Design basic frontend interface for banking operations | COULD HAVE | No Dependency | Adesh Sonawane | 3- Completed
S8 | S8 | US-12 | Connect frontend with backend APIs for smooth data flow | SHOULD HAVE | US-11 | Adesh Sonawane | 3- Completed
S8 | S8 | US-13 | Conduct end-to-end testing to verify complete application functionality | SHOULD HAVE | US-12 | Adesh Sonawane | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 71 | 29 | 27 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Set up development environment - Install Java 17, Maven, VS Code, Spring Boot CLI, MongoDB, and configure required database connectivity | 2025-02-17 | 2025-02-18 | Adesh Sonawane | Setup | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Learn core OOP concepts in Java - Understand classes, objects, encapsulation, inheritance, polymorphism, and abstraction for banking application design | 2025-02-19 | 2025-02-20 | Adesh Sonawane | Design | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Prepare workflow and project documentation - Define system modules, data flow, and key features for the Banking Activity Simulation Platform | 2025-02-21 | 2025-02-21 | Adesh Sonawane | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 4 | Initialize Spring Boot project - Create Maven project, configure application settings, and organize packages (controller, service, model, repository) | 2025-02-24 | 2025-02-25 | Adesh Sonawane | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 5 | Develop Account model - Create a Java class with fields like accountId, holderName, balance, and status using encapsulation principles | 2025-02-26 | 2025-02-28 | Adesh Sonawane | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 6 | Build AccountService layer - Implement business logic for account creation, retrieval, balance update, and deletion operations | 2025-03-03 | 2025-03-04 | Adesh Sonawane | Coding | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 7 | Create Account Controller - Develop REST APIs for account operations and test endpoints using Postman | 2025-03-05 | 2025-03-07 | Adesh Sonawane | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 8 | Design MongoDB database structure - Create collections for accounts and transactions and integrate MongoDB with Spring Boot | 2025-03-10 | 2025-03-12 | Adesh Sonawane | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 9 | Implement deposit feature - Add functionality to credit amount into account and store transaction details in database | 2025-03-17 | 2025-03-18 | Adesh Sonawane | Coding | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 10 | Implement withdrawal feature - Deduct balance with proper validation and update transaction records | 2025-03-19 | 2025-03-21 | Adesh Sonawane | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 11 | Develop fund transfer feature - Enable money transfer between accounts with necessary checks and transaction logging | 2025-03-24 | 2025-03-26 | Adesh Sonawane | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 12 | Handle transaction validations and exceptions - Manage invalid inputs, insufficient balance, and runtime errors effectively | 2025-03-31 | 2025-04-01 | Adesh Sonawane | Coding | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 13 | Develop balance alert module - Generate alerts when account balance falls below a specified limit | 2025-04-01 | 2025-04-02 | Adesh Sonawane | Design | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 14 | Build frontend user interface - Design UI for performing account and transaction operations | 2025-04-02 | 2025-04-02 | Adesh Sonawane | Integration | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 15 | Integrate frontend with backend and perform testing - Connect APIs with UI and validate complete system through end-to-end testing | 2025-04-02 | 2025-04-02 | Adesh Sonawane | Testing | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Initial confusion about project scope and requirements | Discussed with mentor and clarified overall project objectives
Sprint 1 | Day 4 | Lack of clarity in account module design and workflow | Conducted team discussion and finalized system structure
Sprint 2 | Day 6 | Difficulty understanding API structure and flow | Reviewed documentation and resolved doubts with mentor support
Sprint 2 | Day 7 | Challenges identifying complete account operations | Performed research and refined use case definitions
Sprint 2 | Day 9 | Confusion in feature prioritization | Prepared a priority list based on core banking functionality
Sprint 3 | Day 12 | Errors while implementing account retrieval APIs | Debugged and tested APIs using multiple scenarios
Sprint 4 | Day 16 | Issues in deposit logic implementation | Corrected balance calculations and validated results
Sprint 5 | Day 20 | Problems handling withdrawal edge cases | Enhanced validation logic and handled boundary conditions
Sprint 5 | Day 23 | Difficulty implementing fund transfer functionality | Tested multiple account scenarios and refined transfer logic
Sprint 6 | Day 26 | Incomplete exception handling in transactions | Implemented proper error handling and improved system stability
Sprint 7 | Day 29 | Challenges developing balance alert feature | Improved threshold logic and completed alert implementation
Sprint 7 | Day 31 | Issues integrating frontend with backend APIs | Fixed API responses and ensured smooth data exchange
Sprint 8 | Day 36 | Minor bugs found during integration testing | Debugged and resolved remaining issues
Sprint 8 | Day 40 | Inconsistencies during final testing phase | Performed end-to-end testing and verified complete system

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-02-17 | 2025-02-21 | Adesh Sonawane | Start proper project planning and requirement analysis | Avoid unclear understanding of requirements | Continue regular mentor discussions | Documented clear project scope and workflow
2 | Sprint 2 | 2025-02-24 | 2025-02-28 | Adesh Sonawane | Start structured API development approach | Stop working without proper design planning | Continue writing clean and modular code | Prepared API design and validation strategy
3 | Sprint 3 | 2025-03-03 | 2025-03-07 | Adesh Sonawane | Start testing APIs with multiple scenarios | Stop ignoring edge cases during development | Continue debugging practices | Improved API testing and error handling
4 | Sprint 4 | 2025-03-10 | 2025-03-14 | Adesh Sonawane | Start optimizing logic for better performance | Stop inefficient logic implementation | Continue validating outputs | Optimized logic and fixed calculation issues
5 | Sprint 5 | 2025-03-17 | 2025-03-21 | Adesh Sonawane | Start handling edge cases in transactions | Stop incomplete validation checks | Continue improving business logic | Enhanced validation for withdrawal and transfer
6 | Sprint 6 | 2025-03-24 | 2025-03-28 | Adesh Sonawane | Start implementing proper exception handling | Stop ignoring runtime errors | Continue improving system stability | Added exception handling and improved error messages
7 | Sprint 7 | 2025-03-31 | 2025-04-02 | Adesh Sonawane | Start focusing on integration and UI improvements | Stop delaying frontend integration | Continue testing integrated modules | Completed frontend integration successfully
8 | Sprint 8 | 2025-03-31 | 2025-04-02 | Adesh Sonawane | Start thorough end-to-end testing | Stop skipping final validations | Continue debugging and performance checks | Performed complete system testing and fixed final bugs